## Project Management Plan
Yearly Goal | Complete building CI-CD pipeline
Week | Task | Complexity
Q1 Goal | Setup project plan and development environment
2023-01-01 | Create project plan in spreadsheet | Medium
2023-01-08 | Create a Trello board for task tracking | Low
2023-02-01 | Create the Cloud-Based Development Environment | Medium
2023-02-08 | Create Project Scaffolding | Medium
2023-03-01 | Do Local Test | Low
Q2 Goal | Configure Coninious Integration on Github
2023-04-01 | Enable Github Actions | Medium
2023-04-09 | Configure Python application test with Github Actions | Medium
2023-05-01 | Verify Remote Tests pass | Low
Q3 Goal | Configure Continious Delivery on Azure
2023-07-01 | Add Flask Starter Code to project | Medium
2023-07-10 | Testing of Making predictions | Medium
2023-08-01 | Inspecting the logs | Low
2023-08-07 | Load test application using Locust | High
2023-09-01 | Use Azure CLI to deploy and manage the application | High
Q4 Goal | Demo project work
2023-12-01 | Create technical documentation with README | High
2023-12-15 | Create a demo video showing how the project works | High